## Slide 1: More information on Kaizen Events
Planning a Kaizen Event
1. Define objectives and scope
2. Identify team members (6-12 people)
3. Gather data and metrics
4. Schedule event (2-5 days)
5. Prepare agenda and materials

## Slide 2: Kaizen Event Agenda
Day 1:
1. Introduction and training
2. Problem definition and analysis
3. Data review and goal-setting
Day 2:
1. Root cause analysis
2. Solution generation
3. Idea prioritization

## Slide 3: Kaizen Event Agenda
Day 3:
1. Solution design and prototyping
2. Implementation planning
Day 4-5:
1. Implementation and testing
2. Evaluation and feedback

## Slide 4: Kaizen Event Tools
1. Fishbone Diagrams (Ishikawa)
2. Pareto Analysis
3. Value Stream Mapping
4. Brainstorming
5. PDCA (Plan-Do-Check-Act) cycle
6. SWOT Analysis
7. Root Cause Analysis

## Slide 5: Kaizen Event Roles
1. Facilitator
2. Team Leader
3. Sponsor
4. Team Members
5. Subject Matter Experts

## Slide 6: Kaizen Event Challenges
1. Resistance to change
2. Limited resources
3. Difficulty sustaining improvements
4. Insufficient training
5. Poor communication

## Slide 7: Overcoming Challenges
1. Effective communication
2. Stakeholder engagement
3. Continuous training
4. Regular feedback
5. Celebration of successes

## Slide 8: Kaizen Event Metrics
1. Lead time reduction
2. Productivity increase
3. Quality improvement
4. Cost savings
5. Employee engagement

## Slide 9: Case Study Examples
1. Hospital reduces patient wait time by 40%
2. Manufacturing plant increases productivity by 25%
3. Software company reduces defect rate by 30%